## Resource Tracker
Category | Resource Name | Resource ID / ARN | Type / Details | Status | Notes
VPC & NETWORKING
VPC | linkedeye-shared-vpc | vpc-01d43b65392eb7364 | 10.15.0.0/16 | Done | Primary VPC
Public Subnet AZ1a | linkedeye-public-az1 | subnet-0bdc4533ee62b2d3c | 10.15.1.0/24 (ap-south-1a) | Done | EKS nodes, ALB
Public Subnet AZ1b | linkedeye-public-az2 | subnet-054e0299c17cd8792 | 10.15.2.0/24 (ap-south-1b) | Done | ALB 2nd AZ
Private Subnet AZ1a | linkedeye-private-az1 | subnet-0f5887a9f7bd825d6 | 10.15.10.0/24 (ap-south-1a) | Done | EKS control plane ENIs
Private Subnet AZ1b | linkedeye-private-az2 | subnet-05cd5f6bf97410bc5 | 10.15.11.0/24 (ap-south-1b) | Done | EKS control plane ENIs
Storage Subnet AZ1a | linkedeye-storage-az1 | subnet-05bc39de32b347f04 | 10.15.20.0/24 (ap-south-1a) | Done | Reserved for storage
Storage Subnet AZ1b | linkedeye-storage-az2 | subnet-0fba24a417964ab69 | 10.15.21.0/24 (ap-south-1b) | Done | Reserved for storage
Internet Gateway | linkedeye-igw | igw-02b8ef9f5e002f482 | Attached to VPC | Done
NAT Gateway | — | — | — | Pending | Not yet deployed
VPC Flow Logs | linkedeye-flowlogs | fl-0118e55d4a7b3a88d | ALL traffic → /aws/vpc/flowlogs/linkedeye (90d) | Done
SECURITY GROUPS
SG | linkedeye-eks-cluster-sg | sg-07e2a335b24ecaac1 | EKS Control Plane API access | Done
SG | eks-cluster-sg-linkedeye-... | sg-0a2af945be1848556 | EKS managed ENI SG (auto-created) | Done
SG | linkedeye-eks-hybrid-sg | sg-0fe5d6167a67aedc2 | Hybrid node traffic via VPN | Done
SG | linkedeye-jenkins-ec2-sg | sg-01b7dc73be9af932d | Jenkins EC2 — CI/CD builds | Done
SG | linkedeye-mgmt-ec2-sg | sg-0ff7d92d72838ea12 | Mgmt+ITSM EC2 — all tools | Done
SG | linkedeye-alb-sg | sg-01f66568ac2628a64 | ALB — public HTTPS | Done
SG | GuardDutyManaged... | sg-016c2c8a586bb2025 | GuardDuty auto-managed | Done | Auto-created
EKS CLUSTER
EKS Cluster | linkedeye-finspot-k8s-cluster | — | K8s v1.34 (control plane), logging disabled | Done | Upgraded 2026-03-30: 1.31→1.32→1.33→1.34
Node Group (deleted) | le-jenkins-ng | i-04392efbb3e604d66 | m5.xlarge, AL2 — DELETED 2026-03-30 | Deleted | Merged into le-mgmt-tools-ng-v2
Node Group | le-mgmt-tools-ng-v2 | eks-le-mgmt-tools-ng-v2-2ece838f-be29-bd78-d854-fa41dd941cd7 | 2x m5.xlarge, AL2, 2/2/2 (min/desired/max) — nodes at v1.31 | Done | Labels: role=mgmt-tools, jenkins=true. Node upgrade to v1.34 needs AL2023 AMI.
Addon | vpc-cni | — | v1.20.4-eksbuild.2 | Done
Addon | coredns | — | v1.11.3-eksbuild.1 | Done
Addon | kube-proxy | — | v1.31.10-eksbuild.12 | Done
Addon | aws-ebs-csi-driver | — | v1.38.1-eksbuild.2 | Done
Addon | aws-guardduty-agent | — | v1.12.1-eksbuild.2 | Done
Hybrid Nodes | On-prem workers (15 clients) | — | SSM Hybrid Activation, public API | Pending | No VPN needed
Client Namespaces | 15 prod + 3 non-prod | — | Per-client isolation | Script Ready | 06-kubernetes/11
LOAD BALANCER & TARGET GROUPS
ALB | linkedeye-tools-alb | linkedeye-tools-alb-922526253.ap-south-1.elb.amazonaws.com | internet-facing, AZ1a+AZ1b | Done | Created 2026-03-12
EIP | ALB EIP 1 | eipalloc-02539b2e34bf4a3c3 | 3.109.131.36 | Done | ALB ENI
EIP | ALB EIP 2 | eipalloc-0dee5cf69fb919765 | 43.205.77.93 | Done | ALB ENI
Target Group | linkedeye-tg-jenkins | — | Port 8080, HTTP, instance | Done
Target Group | linkedeye-tg-argocd | — | Port 8082, HTTP, instance | Done
Target Group | linkedeye-tg-harbor | — | Port 8083, HTTP, instance | Done
Target Group | linkedeye-tg-keycloak | — | Port 8081, HTTP, instance | Done
Target Group | linkedeye-tg-vault | — | Port 8200, HTTP, instance | Done
Target Group | linkedeye-tg-itsm | — | Port 80, HTTP, instance | Done
Target Group | linkedeye-tg-client-itsm | — | Port 80, HTTP, instance | Done | Client FQDN routing
Target Group | linkedeye-tg-minio | — | Port 30901, HTTP, instance | Done
Client ALB Rules | 15 client FQDNs | — | fs-le-*.finspot.in host routing | Script Ready | 05-loadbalancer/02
IAM ROLES
IAM Role | linkedeye-eks-cluster-role | arn:aws:iam::654697417727:role/linkedeye-eks-cluster-role | EKS cluster service role | Done | 2026-03-12
IAM Role | linkedeye-eks-nodegroup-role | arn:aws:iam::654697417727:role/linkedeye-eks-nodegroup-role | EKS managed node group role | Done | 2026-03-12
IAM Role | linkedeye-eks-hybrid-node-role | arn:aws:iam::654697417727:role/linkedeye-eks-hybrid-node-role | Hybrid on-prem node role | Done | 2026-03-15
IAM Role | linkedeye-mgmt-ec2-role | arn:aws:iam::654697417727:role/linkedeye-mgmt-ec2-role | Mgmt EC2 instance role | Done | 2026-03-12
IAM Role | linkedeye-container-insights-role | arn:aws:iam::654697417727:role/linkedeye-container-insights-role | CloudWatch Container Insights | Done | 2026-03-10
IAM Role | linkedeye-velero-irsa-role | arn:aws:iam::654697417727:role/linkedeye-velero-irsa-role | Velero IRSA for S3 backup | Done | 2026-03-10
SECURITY & ENCRYPTION
KMS Key | linkedeye-kms-eks | 79f25c77-3399-457e-9981-61ab6a59440f | EKS secrets encryption | Done
KMS Key | linkedeye-kms-vault | 6e42d4e7-7d23-48c3-9956-47e3e3ec79f0 | Vault auto-unseal | Done
KMS Key | linkedeye-kms-ebs | c58c1e22-a9a7-48f3-a5f1-f50d67c6695e | EBS volume encryption | Done
WAF | linkedeye-waf | c125267b-4e92-4c24-8a03-88eddcdc3be7 | 4 rules: CommonRuleSet, KnownBadInputs, SQLi, RateLimit | Done | Attached to ALB
GuardDuty | Detector | fa47792e40684b45bfa76c1b4a1a48a4 | Threat detection | Done
STORAGE & LOGGING
S3 Bucket | linkedeye-velero-backups-654697417727 | — | Velero cluster backups | Done | Created 2026-03-10
S3 Bucket | linkedeye-audit-logs-654697417727 | — | CloudTrail audit logs | Done | Created 2026-03-10
CloudWatch Logs | /aws/eks/linkedeye-finspot-k8s-cluster/cluster | — | EKS control plane logs — DISABLED 2026-03-30 | Disabled | Logging disabled to reduce CW costs
CloudWatch Logs | /aws/vpc/flowlogs/linkedeye | — | VPC flow logs (23 MB, 90-day retention) | Done
ORPHANED RESOURCES (needs cleanup)
CloudWatch Logs | /aws/eks/le-shared-eks/cluster | — | 173 MB from deleted cluster | Orphan — Delete | Need logs:DeleteLogGroup permission
KMS Key | (alias removed, unnamed) | d514cb7e-6ce0-4d17-a42d-a0311ded34d0 | Unused EKS secrets key | Orphan — Disable/Delete | Need kms:ScheduleKeyDeletion
VPC | finspot-cloud | vpc-0bd83076448a26cec | 11.0.0.0/24, empty except EFS mount | Orphan — Delete | Need efs:DeleteMountTarget first

## Deployment Checklist
Phase | Step | Script | Description | Status | Notes
A — Network | 1 | 01-network/01-create-vpc.sh | Create VPC, subnets, IGW, enable DNS | Done | VPC vpc-01d43b65392eb7364
A — Network | 2 | 01-network/02-create-nat-gateway.sh | Create NAT Gateway in public subnet | Pending
A — Network | 3 | 01-network/03-create-security-groups.sh | Create base security groups | Done
A — Network | 4 | 01-network/04-create-vpn.sh | VPN to FortiGate (on-prem) | Skip | Not needed — public EKS API
A — Network | 5 | 01-network/05-tag-subnets-for-eks.sh | Tag private subnets for EKS ENIs | Done
A — Network | 6 | 01-network/06-create-eks-security-groups.sh | Create EKS-specific security groups | Done
A — IAM | 1 | 02-iam/01-create-iam-roles.sh | Create base IAM roles | Done | Old bastion/master/worker roles deleted
A — IAM | 2 | 02-iam/02-create-eks-iam-roles.sh | Create EKS cluster + node + IRSA roles | Done
A — IAM | 3 | 02-iam/03-create-mgmt-ec2-role.sh | Create mgmt EC2 instance role | Done
B — Compute | 1 | 04-compute/01-create-key-pair.sh | Create SSH key pair | Done | ~/.ssh/le-shared-k8s-key.pem
B — Compute | 5 | 04-compute/05-launch-jenkins-ec2.sh | Launch Jenkins EC2 | Done (via EKS) | Now EKS node group le-jenkins-ng
B — Compute | 6 | 04-compute/06-launch-mgmt-ec2.sh | Launch Mgmt EC2 | Done (via EKS) | Now EKS node group le-mgmt-tools-ng-v2
C — EKS | 4 | 06-kubernetes/04-create-eks-cluster.sh | Create EKS cluster (hybrid mode) | Done | v1.31, linkedeye-finspot-k8s-cluster
C — EKS | 5 | 06-kubernetes/05-setup-hybrid-nodes.sh | SSM Hybrid Activation for on-prem | Pending | 15 clients, 2 nodes each
C — EKS | 6 | 06-kubernetes/06-install-eks-addons.sh | Install EKS addons | Done | vpc-cni, coredns, kube-proxy, ebs-csi, guardduty
C — EKS | 7 | 06-kubernetes/07-install-alb-controller.sh | Install ALB Ingress Controller | Pending | Optional
C — EKS | 8 | 06-kubernetes/08-configure-eks-access.sh | Configure kubeconfig + aws-auth | Done
C — EKS | 11 | 06-kubernetes/11-create-client-namespaces.sh | Create per-client namespaces | Script Ready | 15 prod + 3 non-prod
F — ALB | 1 | 05-loadbalancer/01-create-alb-for-tools.sh | Create ALB for management tools | Done | linkedeye-tools-alb
F — ALB | 2 | 05-loadbalancer/02-add-client-alb-rules.sh | Add client FQDN host routing | Script Ready | 15 client FQDNs
X — Enterprise | 1 | 12-enterprise/01-create-kms-keys.sh | Create 3 KMS keys (EKS, Vault, EBS) | Done | Annual rotation enabled
X — Enterprise | 2 | 12-enterprise/02-enable-eks-encryption.sh | EKS envelope encryption | Pending | EKS encryption config is null
X — Enterprise | 3 | 12-enterprise/03-enforce-imdsv2.sh | Enforce IMDSv2 on EC2s | Pending
X — Enterprise | 4 | 12-enterprise/04-apply-pod-security-standards.sh | K8s Pod Security Standards | Pending
X — Enterprise | 5 | 12-enterprise/05-configure-rbac.sh | RBAC per-client namespace | Pending
X — Enterprise | 6 | 12-enterprise/06-configure-vault-tls-autounseal.sh | Vault TLS + KMS auto-unseal | Pending
X — Enterprise | 7 | 12-enterprise/07-enable-vpc-flow-logs.sh | VPC Flow Logs | Done | fl-0118e55d4a7b3a88d
X — Enterprise | 8 | 12-enterprise/08-enable-guardduty.sh | Enable GuardDuty | Done | Detector active
X — Enterprise | 9 | 12-enterprise/09-enable-container-insights.sh | Container Insights | Pending
X — Enterprise | 10 | 12-enterprise/10-apply-resource-quotas.sh | K8s resource quotas | Pending
X — Enterprise | 11 | 12-enterprise/11-deploy-prometheus-grafana.sh | Prometheus + Grafana + Alertmanager | Pending
X — Enterprise | 12 | 12-enterprise/12-deploy-external-secrets.sh | External Secrets Operator | Pending
X — Enterprise | 13 | 12-enterprise/13-setup-velero-backup.sh | Velero backup to S3 | Done | S3 bucket created
X — Enterprise | 14 | 12-enterprise/14-enable-waf.sh | WAF on ALB | Done | 4 rules active
X — Enterprise | 15 | 12-enterprise/15-enable-ebs-encryption.sh | EBS encryption | Pending
X — Enterprise | 16 | 12-enterprise/16-enhance-audit-logging.sh | CloudTrail audit logging | Done | S3 audit bucket created
V — Validate | 1 | 10-validation/01-validate-all.sh | Full deployment validation | Pending | Run after all phases
H — Cleanup | 1 | 11-cleanup/01-terminate-old-ec2s.sh | Terminate old kubeadm EC2s | Done | Already terminated

## Tools & Services
Tool | Runs On | Port | FQDN | Target Group | Status | Notes
Jenkins | le-jenkins-ng (m5.xlarge) | 8080 | jenkins.finspot.in | linkedeye-tg-jenkins | Done | CI/CD pipeline
ArgoCD | le-mgmt-tools-ng-v2 (m5.xlarge) | 8082 | argocd.finspot.in | linkedeye-tg-argocd | Done | GitOps deployment
Harbor | le-mgmt-tools-ng-v2 | 8083 | harbor.finspot.in | linkedeye-tg-harbor | Done | Container registry
Keycloak | le-mgmt-tools-ng-v2 | 8081 | keycloak.finspot.in | linkedeye-tg-keycloak | Done | SSO / Identity
Vault | le-mgmt-tools-ng-v2 | 8200 | vault.finspot.in | linkedeye-tg-vault | Done | Secrets management
ITSM | le-mgmt-tools-ng-v2 | 80 | fs-le-*.finspot.in | linkedeye-tg-itsm | Done | LinkedEye ITSM app
Client ITSM | le-mgmt-tools-ng-v2 | 80 | fs-le-{client}.finspot.in | linkedeye-tg-client-itsm | Script Ready | 15 client FQDNs
MinIO | le-mgmt-tools-ng-v2 | 30901 | — | linkedeye-tg-minio | Done | Object storage
Prometheus | EKS (kube-prometheus-stack) | 9090 | — | — | Pending | 12-enterprise/11
Grafana | EKS (kube-prometheus-stack) | 3000 | grafana.finspot.in | — | Pending | 12-enterprise/11
Alertmanager | EKS (kube-prometheus-stack) | 9093 | — | — | Pending | → StackStorm st2api:9101
Velero | EKS | — | — | — | Done | S3 backup bucket created
External Secrets | EKS | — | — | — | Pending | Vault → K8s sync
GuardDuty Agent | EKS Addon | — | — | — | Done | v1.12.1
Container Insights | EKS | — | — | — | Pending | CloudWatch monitoring

## Deleted Resources
Resource Type | Name / ID | Reason Deleted | Deleted On | Deleted By
IAM Role | linkedeye-bastion-role | No bastion in architecture | 2026-03-30 | Claude Code
IAM Role | linkedeye-k8s-master-role | Old kubeadm — replaced by EKS managed | 2026-03-30 | Claude Code
IAM Role | linkedeye-k8s-worker-role | Old kubeadm — replaced by EKS node groups | 2026-03-30 | Claude Code
KMS Alias | alias/linkedeye-eks-secrets | Duplicate unused EKS key alias | 2026-03-30 | Claude Code
EC2 Instance | i-0254e6bd512f67dd9 (old kubeadm master) | Old cluster terminated | Before 2026-03-30 | Manual
EC2 Instance | i-0e0662a64aa8cc8e6 (old kubeadm worker) | Old cluster terminated | Before 2026-03-30 | Manual
File | ~$nkedEye_Prometheus_Runbook.docx | MS Office temp lock file | 2026-03-30 | Claude Code
File | 1 (stale CLAUDE.md copy) | Accidental file creation | 2026-03-30 | Claude Code
File | LinkedEye_Project_Flow_Components (1).html | Duplicate download | 2026-03-30 | Claude Code
Directory | 09-tls/ (empty) | TLS via ACM on ALB, not self-managed | 2026-03-30 | Claude Code

## Credentials & Access
Tool / Service | Username | Password / Token | Internal URL | External URL / FQDN | Notes
TOOL CREDENTIALS
Jenkins | admin | LinkedEye@2026 | http://jenkins.le-cicd.svc.cluster.local:8080 | jenkins.finspot.in:8080 | CI/CD pipeline
ArgoCD | admin | dOBfymX-WKQyfSCh | http://argocd-server.le-cicd.svc.cluster.local:80 | argocd.finspot.in:8082 | GitOps deployment
Harbor | admin | LinkedEye@2026 | http://harbor.le-cicd.svc.cluster.local:80 | harbor.finspot.in:8083 | Container registry
Keycloak | admin | LinkedEye@2026 | http://keycloak.le-security.svc.cluster.local:8080 | keycloak.finspot.in:8081 | SSO / Identity
Vault | (root token) | hvs.ElC1zk6767GBucJIHv1rGTtA | http://vault.le-security.svc.cluster.local:8200 | vault.finspot.in:8200 | Secrets management
MinIO | minioadmin | LinkedEye@2026 | API: http://minio.le-cicd.svc.cluster.local:9000 Console: http://minio-console.le-cicd.svc.cluster.local:9001 | minio:30901 | S3-compatible storage
VAULT UNSEAL KEYS (need 3 of 5 to unseal)
Vault Unseal Key 1 | — | BqZoXTIthvFWgo+IscOO7ghCJG4SwWQLyX1fRHV7tdUu | — | —
Vault Unseal Key 2 | — | up5Ds5eq653AlzbZCP0wTcCTNtV7kPQCgPf8zxjaw0Tl | — | —
Vault Unseal Key 3 | — | QlLz9MGVAjLsJSy10G51eIO3H3N1Jzqf7nM/rY1NpqEq | — | —
Vault Unseal Key 4 | — | BoraPuxBHBFqVM9jolzr0lF3pcnif7n4QkYdb3MFMpQV | ��� | —
Vault Unseal Key 5 | — | rbUVgvlqTszwP0c1xOwTFjTn/VsaDBrrVuEXBaL0So6K | — | —
Vault Root Token | — | hvs.ElC1zk6767GBucJIHv1rGTtA | ��� | —
POSTGRESQL DATABASE CREDENTIALS
PostgreSQL Admin | linkedeye_admin | LinkedEye@DB2026 | postgresql.le-cicd.svc.cluster.local:5432 | — | Centralized DB host
keycloak_db | keycloak_user | Keycloak@DB2026 | postgresql:5432/keycloak_db | —
harbor_core | harbor_user | Harbor@DB2026 | postgresql:5432/harbor_core | —
harbor_notary_server | harbor_user | Harbor@DB2026 | postgresql:5432/harbor_notary_server | —
harbor_notary_signer | harbor_user | Harbor@DB2026 | postgresql:5432/harbor_notary_signer | —
argocd_db | argocd_user | ArgoCD@DB2026 | postgresql:5432/argocd_db | —
vault_db | vault_user | Vault@DB2026 | postgresql:5432/vault_db | —
jenkins_db | jenkins_user | Jenkins@DB2026 | postgresql:5432/jenkins_db | —
SSH ACCESS
SSH Key | ubuntu | ~/.ssh/le-shared-k8s-key.pem | — | — | Key pair: le-shared-k8s-key
Jenkins Node (le-jenkins-ng) | ubuntu | (SSH key) | 10.15.1.63 | 13.234.186.71 | i-04392efbb3e604d66
Mgmt Node (le-mgmt-tools-ng-v2) | ubuntu | (SSH key) | 10.15.1.169 | 3.110.213.19 | i-08a738a53ecf2259d
AWS ACCOUNT ACCESS
AWS Console | rajkumar.madhu@finspot.in | (IAM user) | — | https://654697417727.signin.aws.amazon.com/console | Region: ap-south-1
AWS CLI | AKIAZQ3YBZP7VVP6B4JB | (in ~/.aws/credentials) | — | — | aws cli at ~/bin/aws
ALB ENDPOINTS (linkedeye-tools-alb)
ALB DNS | — | — | — | linkedeye-tools-alb-922526253.ap-south-1.elb.amazonaws.com | internet-facing
ALB EIP 1 | — | — | — | 3.109.131.36 | eipalloc-02539b2e34bf4a3c3
ALB EIP 2 | — | — | — | 43.205.77.93 | eipalloc-0dee5cf69fb919765
VAULT UNSEAL PROCEDURE (after restart)
Step 1 | — | — | SSH to any EKS node | — | ssh -i ~/.ssh/le-shared-k8s-key.pem ubuntu@<node-ip>
Step 2 | — | — | kubectl exec -n le-security vault-0 -- vault operator unseal <key1> | — | Run with 3 different unseal keys
Step 3 | — | — | kubectl exec -n le-security vault-0 -- vault operator unseal <key2> | —
Step 4 | — | — | kubectl exec -n le-security vault-0 -- vault operator unseal <key3> | —
Step 5 (verify) | — | — | kubectl exec -n le-security vault-0 -- vault status | — | Sealed should be false
DATABASE BACKUP
PostgreSQL Backup | — | — | CronJob: daily at 2:00 AM | MinIO bucket: le-db-backups | Manifest: manifests/postgresql/postgresql-backup-cronjob.yaml

## Cost Details
LinkedEye AWS Cost Report — March 2026 (Estimated)
AWS Service | March 2026 (USD) | % of Total | Resource | Usage | Optimization Notes
Amazon EC2 — Compute | 322.93 | 37.0% | 2x m5.xlarge (node groups) + m5.2xlarge + m5.4xlarge | 853h m5.xlarge, 174h m5.2xlarge, 97h m5.4xlarge | m5.4xlarge terminated mid-month; consider Reserved Instances for steady-state nodes
Amazon EKS — Control Plane | 44.65 | 5.1% | linkedeye-finspot-k8s-cluster | 446 cluster-hours | Fixed $0.10/hr — no optimization possible
Amazon EKS — Extended Support | 223.26 | 25.6% | EKS v1.31 extended support surcharge | 446 hours @ $0.50/hr | UPGRADE to v1.32+ when available to exit extended support ($0.50/hr savings)
Amazon EKS — Hybrid Nodes | 53.05 | 6.1% | On-prem hybrid node vCPU hours | 2,652 vCPU-hours | Scales with client count; currently 15 clients
EC2 Other (EBS) | 35.66 | 4.1% | gp3: 322GB, gp2: 54GB | 50GB + 100GB node disks + snapshots | Migrate gp2 → gp3 for cost savings
Elastic Load Balancing | 12.93 | 1.5% | linkedeye-tools-alb | 541 ALB-hours | Fixed cost — single ALB is efficient
Amazon VPC (Public IPv4) | 12.75 | 1.5% | 2 ALB EIPs + node public IPs | 2,549 IP-hours | Release unused EIPs if any
Amazon VPC (NAT Gateway) | 18.76 | 2.2% | NAT Gateway hours | 335 hours | NAT GW not in state table — verify if still needed
Amazon CloudWatch | 10.33 | 1.2% | VPC Flow Logs, EKS logs | 20.4 GB vended logs | Set retention on EKS logs (currently unlimited — 2.98 GB growing)
AWS WAF | 5.35 | 0.6% | linkedeye-waf (4 rules) | 1 WebACL + 4 rules | Standard pricing — already minimal
AWS KMS | 0.65 | 0.1% | 3 keys (EKS, Vault, EBS) | 3 active keys | Delete orphaned key d514cb7e to save $1/mo
Amazon S3 | 0.09 | 0.0% | Velero + Audit log buckets | Minimal storage
AWS CloudTrail | 0 | 0.0% | Audit logging | — | Free tier
Amazon GuardDuty | 0 | 0.0% | Threat detection | — | Free tier / trial
Amazon EFS | 0 | 0.0% | fs-50094f81 (finspot-cloud VPC) | Minimal | Orphaned — delete when possible
Tax (GST 18%) | 133.34 | 15.3% | India GST on AWS services | —
TOTAL (March 2026 estimated) | 873.75 | 100%
DAILY SPEND TREND — March 2026
Date | Daily Cost (USD) | Cumulative (USD) | Notes
2026-03-01 | 133.34 | 133.34 | Tax payment
2026-03-02 | 0 | 133.34
2026-03-03 | 0 | 133.34
2026-03-04 | 0 | 133.34
2026-03-05 | 0 | 133.34
2026-03-06 | 0.6 | 133.94 | Initial setup begins
2026-03-07 | 26.75 | 160.69 | VPC + subnets created
2026-03-08 | 33.37 | 194.06
2026-03-09 | 33.37 | 227.43
2026-03-10 | 50.82 | 278.25 | EKS cluster + enterprise setup
2026-03-11 | 32.21 | 310.46
2026-03-12 | 24.46 | 334.92 | EKS addons + ALB + KMS
2026-03-13 | 28.71 | 363.63
2026-03-14 | 28.71 | 392.34
2026-03-15 | 29.65 | 421.99 | Hybrid node role created
2026-03-16 | 32.5 | 454.49
2026-03-17 | 36.57 | 491.06
2026-03-18 | 43.28 | 534.34
2026-03-19 | 41.29 | 575.63 | Node groups launched (peak day)
2026-03-20 | 32.26 | 607.89
2026-03-21 | 31.09 | 638.98 | Steady state begins (~$31/day)
2026-03-22 | 31.13 | 670.11
2026-03-23 | 31.09 | 701.2
2026-03-24 | 31.07 | 732.27
2026-03-25 | 31.07 | 763.34
2026-03-26 | 31.07 | 794.41
2026-03-27 | 31.1 | 825.51
2026-03-28 | 31.08 | 856.59
2026-03-29 | 17.48 | 874.07 | Partial day (billing in progress)
MONTHLY COST PROJECTION
Period | Estimated Cost (USD) | Breakdown | Notes
March 2026 (actual) | 874.08 | 29 days billed so far | Estimated — final bill pending
Steady-state daily run rate | 31.1 | Per day from Mar 21-28 avg | After initial setup costs settled
Projected monthly (30 days) | 933 | $31.10/day x 30 | Excluding tax
Projected monthly (with 18% GST) | 1100.94 | $933 + 18% tax | Full monthly estimate
COST BREAKDOWN (steady state/mo)
EKS Control Plane | 73 | $0.10/hr x 730hr | Fixed
EKS Extended Support | 365 | $0.50/hr x 730hr | LARGEST COST — upgrade EKS to exit
EC2 Nodes (2x m5.xlarge) | 280 | $0.192/hr x 2 x 730hr | Consider Reserved Instances (40% savings)
EKS Hybrid Nodes | 55 | ~15 clients, 2 vCPU each | Scales with clients
EBS Volumes | 30 | 150GB gp3
ALB | 22 | $0.03/hr + LCU | Fixed
CloudWatch Logs | 11 | ~20GB/mo | Set retention to reduce
VPC (Public IPs) | 15 | ~4 public IPv4
WAF | 8 | 1 ACL + 4 rules | Fixed
Other (KMS, S3, etc.) | 5 | Minimal
COST OPTIMIZATION RECOMMENDATIONS
# | Recommendation | Estimated Savings/mo | Priority | Effort | Details
1 | Upgrade EKS v1.31→v1.34 (exit extended support) ✓ DONE 2026-03-30 | 365 | CRITICAL | Medium | EKS v1.31 extended support costs $0.50/hr ($365/mo). Upgrading removes this. Largest single savings.
2 | Delete le-jenkins-ng, consolidate into le-mgmt-tools-ng-v2 ✓ DONE 2026-03-30 | 177 | High | Low | 2x m5.xlarge at RI 1-year no-upfront = ~$0.124/hr (40% off on-demand $0.192/hr). Saves ~$112/mo.
3 | Disable EKS CloudWatch logging (not required) ✓ DONE 2026-03-30 | 7 | Medium | Low | EKS cluster logs at 2.98GB with no retention. Set 30-day retention. aws logs put-retention-policy
4 | Delete orphaned KMS key d514cb7e (needs permission) | 1 | Low | Low | Key d514cb7e (alias removed). Schedule deletion to save $1/mo. Needs kms:ScheduleKeyDeletion.
5 | Delete orphaned CW log group /aws/eks/le-shared-eks (needs permission) | 0.5 | Low | Low | /aws/eks/le-shared-eks/cluster (173MB). Needs logs:DeleteLogGroup permission.
6 | Migrate gp2 → gp3 EBS volumes | 2 | Low | Low | 54GB on gp2 ($0.114/GB) → gp3 ($0.0912/GB). ~15% savings on those volumes.
7 | Verify/remove NAT Gateway if unused | 18.76 | High | Low | NAT GW costs $18.76/mo but private subnets may not need egress. Delete if unused.
8 | Delete finspot-cloud VPC + EFS (needs efs:DeleteMountTarget permission) | 0.5 | Low | Medium | Orphaned VPC with EFS mount. Needs EFS permissions to clean up.
| TOTAL POTENTIAL SAVINGS (remaining: $22.76 after completed items) | 571.76 |  |  | Up to $504/mo = ~46% reduction
APPLIED SAVINGS (2026-03-30) | Action | Monthly Saving (USD)
| EKS v1.31 → v1.34 upgrade (extended support removed) | 365
| le-jenkins-ng node group deleted (2nd m5.xlarge) | 177
| EKS CloudWatch logging disabled | 7
| TOTAL APPLIED SAVINGS | 549